## Gantt Chart
TASK NAME | W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | W9 | W10 | W11 | W12 | W13 | W14 | W15 | W16 | W17 | W18 | W19 | W20 | W21 | W22 | W23 | W24
SYSTEM DESIGN | bar: W1
Game Re-Design | bar: W2 to W4; W9 to W12
Art Assets Creation | bar: W2 to W8
UI/UX Design | bar: W5 to W12
Programming and Development | bar: W5 to W16
Testing and Bug Fixes | bar: W7 to W16
Marketing | bar: W5 to W16
Dodumentation | bar: W17 to W20
Presentation | bar: W21 to W24
Game Designer
Art Director/Artist
Programmer
QA Tester
Project Manager
ALL

## Budget Sheet
BUDGET SHEET
Item | Cost (month) | Total Cost
Game Designer Salary | 5500 | 33000
Art Director/Artist Salary | 7000 | 42000
Lead Developer/Programmer Salary | 7500 | 45000
QA Tester Salary | 4000 | 24000
Project Manager Salary | 6500 | 39000
Software and Tools | 1000 | 6000
Server Hosting | 500 | 3000
Marketing and Promotion | 4000 | 24000
Contingency (10% of total) | N/A | 21600
Total Cost | 36000 | 216000